## ورقة1
Team BackLog
Scope | Task Name | Assignee | Task status | Expected Time to finish | Actual time to finish
High Level Desing | Arch Design | Moustafa AbdElrahim | Done | 4 hrs. | 2 hrs.
Coding | Motor Driver |  | Done | 1 hrs. | 1 hrs.
| Car_Moving_Forward_LongSide | Kareem Magdy | Done | 8 hrs. | 9 hrs.
| Car_Moving_Forward_ShortSide | Amr ElAbd | Done | 8 hrs. | 9 hrs.
| Car_Turns_90_Degree_Calculations | Nada AbdElazim | Done | 3 hrs. | 4 hrs.
| Car_Turns_90_Degree | Nada AbdElazim | Done | 1 hrs. | 1 hrs.
| Start&Stop_Logic | Moustafa AbdElrahim | Done | 1 hrs. | 2 hrs.
| Main_Flow & Simulation Design | Amr ElAbd | Done | 8 hrs. | 8 hrs.
|  | Kareem Magdy |  | 8 hrs. | 8 hrs.
|  | Moustafa AbdElrahim |  | 8 hrs. | 8 hrs.
|  |  |  | 8 hrs. | 2 hrs.
| Code_Indentation | Kareem Magdy | Done | 4 hrs. | 4 hrs.
Documentaion | Test Protcol Sheet | Nada AbdElazim | Done | 2 hrs. | 2 hrs.
| Project Documentaion | Amr ElAbd |  | 4 hrs. | 4 hrs.